## Gantt
Board - HEX 2 - Data Science Project - Team J (by months)
|  |  | Mar-2024 | Mar-2024 | Mar-2024 | Apr-2024 | Apr-2024 | Apr-2024 | Apr-2024 | Apr-2024 | May-2024 | May-2024 | May-2024 | May-2024 | Jun-2024 | Jun-2024 | Jun-2024 | Jun-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Jul-2024 | Aug-2024 | Aug-2024 | Aug-2024 | Aug-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Sep-2024 | Oct-2024 | Oct-2024 | Oct-2024
| Start | End | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21
Team Lead Assigned | 11-Mar-2024 | 11-Mar-2024 | 11: Team Lead Assigned (11-Mar-24 - 11-Mar-24)
GitHub Setup | 11-Mar-2024 | 13-Mar-2024 | 11: GitHub Setup (11-Mar-24 - 13-Mar-24)
Project Plan Created | 12-Mar-2024 | 18-Mar-2024 | 11: Project Plan Created (12-Mar-24 - 18-Mar-24); 18: Project Plan Created (12-Mar-24 - 18-Mar-24)
Discuss with counsellor | 13-Mar-2024 | 13-Mar-2024 | 11: Discuss with counsellor (13-Mar-24 - 13-Mar-24)
Define Project Goal | 14-Mar-2024 | 14-Mar-2024 | 11: Define Project Goal (14-Mar-24 - 14-Mar-24)
Develop Research Questions | 14-Mar-2024 | 14-Mar-2024 | 11: Develop Research Questions (14-Mar-24 - 14-Mar-24)
Role and Activities Assigned | 15-Mar-2024 | 16-Mar-2024 | 11: Role and Activities Assigned (15-Mar-24 - 16-Mar-24)
Identify Datasets | 15-Mar-2024 | 15-Mar-2024 | 11: Identify Datasets (15-Mar-24 - 15-Mar-24)
Write up Assignment 1A | 16-Mar-2024 | 17-Mar-2024 | 11: Write up Assignment 1A (16-Mar-24 - 17-Mar-24)
Collect Data | 18-Mar-2024 | 19-Mar-2024 | 18: Collect Data (18-Mar-24 - 19-Mar-24)
Schedule counsellor Session | 18-Mar-2024 | 18-Mar-2024 | 18: Schedule counsellor Session (18-Mar-24 - 18-Mar-24)
Review Assignment 1A | 18-Mar-2024 | 18-Mar-2024 | 18: Review Assignment 1A (18-Mar-24 - 18-Mar-24)
Submit Assignment 1A | 19-Mar-2024 | 19-Mar-2024 | 18: Submit Assignment 1A (19-Mar-24 - 19-Mar-24)
Preliminary Analysis: Select features, link up data sources, etc. | 20-Mar-2024 | 24-Mar-2024 | 18: Preliminary Analysis: Select features, link up data sources, etc. (20-Mar-24 - 24-Mar-24)
Background research on modelling | 20-Mar-2024 | 24-Mar-2024 | 18: Background research on modelling (20-Mar-24 - 24-Mar-24)
Create Draft Report with Sections | 20-Mar-2024 | 24-Mar-2024 | 18: Create Draft Report with Sections (20-Mar-24 - 24-Mar-24)
Draft literature review section | 23-Mar-2024 | 24-Mar-2024 | 18: Draft literature review section (23-Mar-24 - 24-Mar-24)
Start Modelling and Analysis | 25-Mar-2024 | 31-Mar-2024 | 25: Start Modelling and Analysis (25-Mar-24 - 31-Mar-24)
Create visualisations | 25-Mar-2024 | 31-Mar-2024 | 25: Create visualisations (25-Mar-24 - 31-Mar-24)
Summarise results and meaning | 25-Mar-2024 | 31-Mar-2024 | 25: Summarise results and meaning (25-Mar-24 - 31-Mar-24)
Update Report | 30-Mar-2024 | 01-Apr-2024 | 25: Update Report (30-Mar-24 - 01-Apr-24); 1: Update Report (30-Mar-24 - 01-Apr-24)
Continue Modelling and Analysis | 01-Apr-2024 | 04-Apr-2024 | 1: Continue Modelling and Analysis (01-Apr-24 - 04-Apr-24)
Create visualisations | 04-Apr-2024 | 06-Apr-2024 | 1: Create visualisations (04-Apr-24 - 06-Apr-24)
Summarise results and meaning | 07-Apr-2024 | 08-Apr-2024 | 1: Summarise results and meaning (07-Apr-24 - 08-Apr-24); 8: Summarise results and meaning (07-Apr-24 - 08-Apr-24)
Complete draft report | 08-Apr-2024 | 11-Apr-2024 | 8: Complete draft report (08-Apr-24 - 11-Apr-24)
Update Report | 08-Apr-2024 | 09-Apr-2024 | 8: Update Report (08-Apr-24 - 09-Apr-24)
Complete review of report | 12-Apr-2024 | 15-Apr-2024 | 8: Complete review of report (12-Apr-24 - 15-Apr-24); 15: Complete review of report (12-Apr-24 - 15-Apr-24)
Create Presentation | 15-Apr-2024 | 20-Apr-2024 | 15: Create Presentation (15-Apr-24 - 20-Apr-24)
Finalise report | 16-Apr-2024 | 19-Apr-2024 | 15: Finalise report (16-Apr-24 - 19-Apr-24)
Submit Assignment 3: Group Project Report | 20-Apr-2024 | 20-Apr-2024 | 15: Submit Assignment 3: Group Project Report (20-Apr-24 - 20-Apr-24)
Record Sections | 21-Apr-2024 | 21-Apr-2024 | 15: Record Sections (21-Apr-24 - 21-Apr-24)
Merge Videos | 22-Apr-2024 | 22-Apr-2024 | 22: Merge Videos (22-Apr-24 - 22-Apr-24)
Submit Assignment 4: Group Video Presentation | 23-Apr-2024 | 23-Apr-2024 | 22: Submit Assignment 4: Group Video Presentation (23-Apr-24 - 23-Apr-24)